## Project Plan
*Notes: - Deliveries with testable functionalities are planned almost every week. - For each module, make sure that the functionalities of the Checklist are fulfilled. - You will find relevant data in the TEST DATA tab. | [5 empty] | Catch-up meetings: minimum once per week
PROJECT PLAN
| Nombre | Depende de | Duración | Inicio | Finalización
| dotREZ Migration Igor V2.0 |  | 116 días | 2021-04-12 09:00 | 2021-09-20 17:00
| [NS] Dev local set up |  | 4 días | 2021-04-12 09:00 | 2021-04-15 17:00
| dotREZ Environment is available | 189 - [NS] Dev local set up | 0 días | 2021-04-15 17:00 | 2021-04-15 17:00
| dotREZ Training sessions |  | 3 días | 2021-04-19 09:00 | 2021-04-21 17:00
| [TO] DEV4 available |  | 0 días | 2021-05-10 09:00 | 2021-05-10 09:00
| dotREZ DEV + QA |  | 67 días | 2021-04-16 09:00 | 2021-07-19 17:00
| Booking Flow |  | 31 días | 2021-04-16 09:00 | 2021-05-28 17:00
| Delivery 1 | 189 - [NS] Dev local set up, 190 - dotREZ Environment is available | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| BF1: Trip Types |  | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| BF2: Passenger Types |  | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| BF3: Routes |  | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| BF4: Fares |  | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| BF5: Passenger Information |  | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| BF6: Travel Documents |  | 9 días | 2021-04-16 09:00 | 2021-04-28 17:00
| Delivery 2 | 195 - Delivery 1 | 5 días | 2021-04-29 09:00 | 2021-05-05 17:00
| BF7: Payment |  | 5 días | 2021-04-29 09:00 | 2021-05-05 17:00
| Delivery 3 | 202 - Delivery 2 | 8 días | 2021-05-06 09:00 | 2021-05-17 17:00
| BF8: Baggage |  | 8 días | 2021-05-06 09:00 | 2021-05-17 17:00
| BF9: Meals |  | 8 días | 2021-05-06 09:00 | 2021-05-17 17:00
| BF10: Special Assistance |  | 8 días | 2021-05-06 09:00 | 2021-05-17 17:00
| Delivery 4 | 204 - Delivery 3 | 9 días | 2021-05-18 09:00 | 2021-05-28 17:00
| BF11: Seatmap |  | 9 días | 2021-05-18 09:00 | 2021-05-28 17:00
| BF12: Multicity |  | 9 días | 2021-05-18 09:00 | 2021-05-28 17:00
| BF13: Promocode |  | 9 días | 2021-05-18 09:00 | 2021-05-28 17:00
| Manage my Booking |  | 10 días | 2021-05-31 09:00 | 2021-06-11 17:00
| Delivery 5 | 208 - Delivery 4 | 5 días | 2021-05-31 09:00 | 2021-06-04 17:00
| MMB1: Login |  | 5 días | 2021-05-31 09:00 | 2021-06-04 17:00
| MMB2: Change Flight |  | 5 días | 2021-05-31 09:00 | 2021-06-04 17:00
| MMB3: Payment |  | 5 días | 2021-05-31 09:00 | 2021-06-04 17:00
| MMB4: Baggage |  | 5 días | 2021-05-31 09:00 | 2021-06-04 17:00
| Delivery 6 | 213 - Delivery 5 | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| MMB5: Meals |  | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| MMB6: Special Assistance |  | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| MMB7: Seatmap |  | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| MMB8: Change Contact |  | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| MMB9: Change passenger |  | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| MMB10: Resend Itinerary |  | 5 días | 2021-06-07 09:00 | 2021-06-11 17:00
| Web Check-in |  | 6 días | 2021-06-14 09:00 | 2021-06-21 17:00
| Delivery 7 | 218 - Delivery 6 | 4 días | 2021-06-14 09:00 | 2021-06-17 17:00
| WCI1: Login |  | 4 días | 2021-06-14 09:00 | 2021-06-17 17:00
| WCI2: Select Flight and Passenger |  | 4 días | 2021-06-14 09:00 | 2021-06-17 17:00
| WCI3: Payment |  | 4 días | 2021-06-14 09:00 | 2021-06-17 17:00
| WCI4: Passenger details |  | 4 días | 2021-06-14 09:00 | 2021-06-17 17:00
| Delivery 8 | 226 - Delivery 7 | 2 días | 2021-06-18 09:00 | 2021-06-21 17:00
| WCI5: Baggage |  | 2 días | 2021-06-18 09:00 | 2021-06-21 17:00
| WCI6: Meals |  | 2 días | 2021-06-18 09:00 | 2021-06-21 17:00
| WCI7: Seatmap |  | 2 días | 2021-06-18 09:00 | 2021-06-21 17:00
| WCI8: Boarding Pass |  | 2 días | 2021-06-18 09:00 | 2021-06-21 17:00
| Members |  | 14 días | 2021-06-22 09:00 | 2021-07-09 17:00
| Delivery 9 | 231 - Delivery 8 | 5 días | 2021-06-22 09:00 | 2021-06-28 17:00
| B2C1: Register |  | 5 días | 2021-06-22 09:00 | 2021-06-28 17:00
| B2C2: Login |  | 5 días | 2021-06-22 09:00 | 2021-06-28 17:00
| B2C3: Booking Flow |  | 5 días | 2021-06-22 09:00 | 2021-06-28 17:00
| B2C4: Manage my Booking |  | 5 días | 2021-06-22 09:00 | 2021-06-28 17:00
| B2C5: Web Check-in |  | 5 días | 2021-06-22 09:00 | 2021-06-28 17:00
| Delivery 10 | 237 - Delivery 9 | 3 días | 2021-06-29 09:00 | 2021-07-01 17:00
| B2C6: Profile |  | 3 días | 2021-06-29 09:00 | 2021-07-01 17:00
| B2C7: Contact Details page |  | 3 días | 2021-06-29 09:00 | 2021-07-01 17:00
| Delivery 11 | 243 - Delivery 10 | 6 días | 2021-07-02 09:00 | 2021-07-09 17:00
| B2C8: Travel Document page |  | 6 días | 2021-07-02 09:00 | 2021-07-09 17:00
| B2C9: Booking List |  | 6 días | 2021-07-02 09:00 | 2021-07-09 17:00
| B2C10: Preferences page |  | 6 días | 2021-07-02 09:00 | 2021-07-09 17:00
| B2C11: Forgot and reseat password |  | 6 días | 2021-07-02 09:00 | 2021-07-09 17:00
| Agencies |  | 6 días | 2021-07-12 09:00 | 2021-07-19 17:00
| Delivery 12 | 246 - Delivery 11 | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| B2B1: Login |  | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| B2B2: Booking Flow |  | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| B2B3: Manage my Booking |  | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| B2B4: Web Check-in |  | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| B2B5: Payment |  | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| B2B6: Booking List |  | 5 días | 2021-07-12 09:00 | 2021-07-16 17:00
| Delivery 13 | 257 - B2B5: Payment | 1 día | 2021-07-19 09:00 | 2021-07-19 17:00
| B2B7: Forgot and reset password |  | 1 día | 2021-07-19 09:00 | 2021-07-19 17:00
| B2B8: Agency profile |  | 1 día | 2021-07-19 09:00 | 2021-07-19 17:00
| [NS] QA functional | 261 - B2B8: Agency profile | 10 días | 2021-07-20 09:00 | 2021-08-02 17:00
| [NS] Stabilization | 262 - [NS] QA functional | 10 días | 2021-08-03 09:00 | 2021-08-16 17:00
| [NS] QA regression test | 263 - [NS] Stabilization | 5 días | 2021-08-17 09:00 | 2021-08-23 17:00
| [F3] UAT | 264 - [NS] QA regression test | 10 días | 2021-08-24 09:00 | 2021-09-06 17:00
| [NS] Bug fixing | 265 - [F3] UAT | 10 días | 2021-09-07 09:00 | 2021-09-20 17:00
| [NS] Create Roll-out Plan | 265 - [F3] UAT | 1 día | 2021-09-07 09:00 | 2021-09-07 17:00
| [NS] Go-Live | 266 - [NS] Bug fixing | 0 días | 2021-09-20 17:00 | 2021-09-20 17:00

## Deliveries (hidden)
# | TRIP TYPE | ROUTE | PROMOCODE | PASSENGERS | DATE | FARE | TITLE | NATIONALITY | DOCUMENT TYPE | SERVICES | SEATS | PAYMENT METHOD | Delivery date
Booking FLow
1 | One Way | Domestic |  | 1ADT |  | Fly |  |  | National ID | - | Remove the seat asutoassgined | Without payment
2 | Round Trip | International |  | 2 ADT |  | Departure: Fly Return: Fly |  |  | Passport | - | Remove the seat asutoassgined | MADA (3DS)
3 | Multicity | Domestic |  | 1 ADT + 1 CHD |  | Departure: Fly+ Return: Fly+ |  | Different to arabia saudi | Iqama | Departure/Return: BAG 25kg (included on the fare) | Autoassignment | VISA (NON-3DS)
4 | One Way | International |  | 1 ADT + 1 INF | Departure >48 hrs | Fly + |  |  | Passport | BAG 25kg (included on the fare) Add BAG 15kg | Expeedy Exit seat (orange) | SADAD
5 | Round Trip | Domestic |  | 2 ADT + 1 CHD + 1 INF |  | Departure: Fly Return: Fly+ |  | Different to arabia saudi | Passport | Departure: Add BAG 25kg and Meals Return: BAG 25kg (included on the fare) | Family Seats | MasterCard (3DS)
6 | Multicity | International | X | 2 ADT + 2 CHD + 2 INF | Departure >24 hrs | Departure: Fly+ Return: Fly |  |  | Passport | Departure: BAG 25 (Included on the fare) Return: Meals | Remove the seat asutoassgined | Voucher (Full payment)
7 | One Way | Domestic | X | 1 ADT |  | Fly | MRS |  |  | Add Special Assistance | Ladies only seat Rows 15 and 16 | MADA Declined (select "M" authentication attempted (no CAVV) in the "Authentication result" field VISA (3DS) Full payment
8 | One Way | Domestic |  | 3 ADT | > 24 hrs | Fly+ |  |  | Passport | BAG 25kg (included) Meals (Chicken shawama - greek salad - vegetables noodles) | Remove the seat asutoassgined | Credit Shell (Full payment)
9 | Round Trip | Domestic | x | 1 ADT + 1 INF | Departure < 24 hrs Reurn > 24 hrs | Departure: Fly Return: Fly |  | Different to arabia saudi | Iqama | Departure: Special assistance wheelchair Return: Meals | Standard plus | Credit shell (partial payment) & VISA (non 3DS)
10 | Multicity | International |  | 5 ADT + 4 CHD |  | Departure: Fly Return: Fly |  |  | Passport |  | Family Seats | Voucher (Partial payment) & MADA
MMB - Change Flight
# | CREATION DATE | TRIP TYPE | ROUTE | FARE | SERVICES | NEW DATE | NEW FARE | NEW SERVICES | COMMENTS | Delivery date |  |  | Delivery date
11 | > 2 hrs | One Way | Departure > 90 min | fly | - | After original date | fly | - | Added CHNG
12 | < 2 hrs | Round Trip | Departure > 90 min | Departure: fly Return: fly | Departure: Meals | Departure <24 hrs | Departure: fly+ Return: fly+ | Departure/Return: Baggage 25Kg (Included on the fare) | Not added CHNG
13 | > 2 hrs | Multicity | Departure > 90 min | Departure: fly+ Return: fly | Departure: Baggage 25 Kg (included on the fare) Return: Meals | Return >24 hrs | Departure: fly Return: fly+ | Departure: Baggage 25 Kg (included on the fare) Return: Meals | Added CHNG
14 | > 2 hrs | One Way | Departure < 90 min | - | - | Not allowed to change flight | - | - | -
15 | > 2 hrs | Round Trip | Departure < 90 min Return > 90 min | Departure: fly Return: fly | Departure: Special Assistance Return: Meals | Departure: Not allowe to change flight Return >24 hrs | Departure: - Return: fly+ | Departure: Special Assistance Return: Meals | Added CHNG
16 | > 2 hrs | Multicity | Departure and Return > 90 min Check-in for departure | Departure: fly+ Return: fly | - | Departure: Not allowed to change flight Return: After original date |  |  | Added CHNG
17 |  | One Way | Any route with a declined payment | - | - | Not allowed to change flight | - | - | -
MMB - Change Contact
# | TRIP TYPE | ROUTE | FARE | COMMENTS | Delivery date
18 |  | One Way | Departure > 90 min
|  | Round Trip | Departure > 90 min
|  | Multicity | Departure > 90 min
|  | One Way | Departure < 90 min
19 |  | Round Trip | Departure < 90 min Return > 90 min
20 |  | Multicity | Departure and Return > 90 min Check-in for departure
21 |  | One Way | Any route with a declined payment
22
MMB - Change passenger
23
24
25
26
27

## Checklist plan
MODULE |  | Comments
ALL
BOOKING FLOW
Search
1 | Allow to select flight type: One Way, Roundtrip, Multicity
2 | For Multicity, the origin fot the second flight must be the same than the destination of the first flight and it is not allowed to be edited.
3 | Allow to select domestic routes in origin and destination
4 | Allow to select inernational routes (DXB and KWI) in origin and destination
5 | Allow to select passenger types: ADT, CHD and INF - Maximum 9 passengers between ADT and CHD - No more infants than adults - Child can't travel alone
6 | Allow to select dates
7 | Allow to add a promocode
8 | Show the popup for international routes when the "Let's fly" button is selected
9 | Allow to search flight when the "Let's fly" button is selected
10 | Allow to search flight on the homepage and standalone page
Select Flight
11 | Allow to go to the select flight page throught a deeplink, example: https://www.flyadeal.com/en/booking/select/?origin1=DMM&destination1=JED&departure1=2021-03-21&adt1=1&chd1=0&inf1=0&origin2=JED&destination2=DMM&departure2=2021-03-29&adt2=1&chd2=0&inf2=0&currency=SAR
12 | Show flight information on the header: - Routes / Dates / passengers
13 | Show the booking summary with zero total amount when flight is not selected
14 | Show the "Continue" and "Back" buttons on the header and at the bottom of the page
15 | Show SAR currency for domestic flights
16 | Show currency for international flights - Origin Dubai: AED (Arab Emirate Dirham) - Origin Kuwait: Dinar
17 | Show one section for availability for One Way
18 | Show two sectios for availability for Roundtrip and Multicity
19 | The day selected appears centered in the week calendar with a green line below
20 | Show the flight number and terminal info on the availability section
21 | Show the button "Show next day's flights" and when it is selected the availability for the next day in the week calendar should be shown
22 | Show fly and fly+ fares on availability
23 | Show an informative popup when the "Continue" button is selected without select flights
24 | Show an informative text when there is not availability for the date selected
25 | Show the label "No flights" on the week calendar when there is a day without availability
26 | Show an informative text when a flight is not allowed to be selected due to the departure/arrival date is overlapped
27 | Allow to display the booking summary when the flight are selected
28 | Show the correct information on the booking summary according with the flight selected: Fares and taxes
29 | Infant appears in the booking summary as service
30 | Add to the booking summary Baggage XP15 when fly+ fare is selected
31 | Allow to edit the flight details through the icon located on the header
32 | Show the popup for international routes when the flight is edited through the edit flight icon located on the header
33 | Goes to the passenger page when theflights are selected and the "Continue" button is selected
Passenger
34 | Show the passenger details foms for ADT, CHD and INF
35 | Show the travel document forms for ADT, CHD and INF
36 | Show the contact details form
37 | Show the SMS option selected by default
38 | Show the marketing opt-in option selected by default
39 | Show the Hijri calendar on date of birth and expiry date fields
40 | Show back and continue buttons
41 | Date of birth: infants can't travel when they are less than 8 days
42 | Show Saudi Arabia as default on nationality field for domestic flights
43 | Show Kuwait by default on Nationality field when Kuwait is selected on the origin
44 | Show United Arab Emirates by default on Nationality field when Dubai is selected on the origin
45 | Show National ID number by default for domestic flights in document type field
46 | Show passport by default when nationality different than Saudi Arabia is selected
47 | Don't show Expiry date field when National ID number is selected on Document type
48 | Expiry date can't be lower to the flight date
49 | Travel document iqama is only shown when the nationality is different to saudi arabia
50 | Show the checkbox on contact form to set the contact information with the one added on passenger 1
51 | Add the SMS Fee on the booking summary when the checkbox is selected
52 | Show the popup for yakeen validation when the travel document is incorrect
53 | Yakeen pop up is always shown when the travel document is Foreign passport. The second time it's possible to go to services page
54 | Show an informative popup when the "Continue" button is selected without add the mandatory information
55 | Show an informative popup is an ADT older than 16 is traveling with a CHD and does not allow with the flow
56 | Show Saudi Arabia by default on country of residence on the contact form
57 | Show Saudi arabia by default on the country code field ont he contact form
58 | Go to the services page when the "Continue" button is selected
59 | Add the SSR FEM for a passenger with title MRS, MS or MISS when the continue button is selected.
60 | Add the SSR FEM for a passenger with title MASTER if there is a valid MS/MRS ADT on the booking when the continue button is selected
Services
61 | Show baggage, meals and special assistance cards
62 | Show back and continue buttons
63 | Don't show meals card for a flight with departure date in less than 24 hours
64 | Don't show any value on the booking summary when the service has a fee zero
65 | Show a check icon on the service card when the service is added to the booking
66 | Show a popup when baggage is not selected and the "Continue" button is selected
67 | Show a popup when meals is not selected and the "Continue" button is selected
68 | Go to the Seat Selection page when the "Continue" button is clicked
Baggage
69 | When the baggage card is selected, a popup should be open and show baggage 25 Kg added when fly+ fare is selected on the Select Flight page
70 | When the baggage card is selected a popup should be open with and show baggage 15Kg and 25Kg for each flight and each passenger ADT and CHD SSR: XP15 and XP25
71 | Show 1 Baggage 25Kg added when fly+ is selected without the posibility to remove it
72 | Allow to select max 2 baggage per pax per segment
73 | Disable the "+" icon when the user has selected 2 baggage
74 | Disable the "-" icon when the user has not selected baggage
75 | Show the total amount for the baggage(s) selected
76 | After select the baggage and click on the confirm button, the popup should be closed and the baggage fee should be added on the booking summary
77 | Allow to remove the baggage added during booking flow
Meals
78 | When the meals card is selected, the meals page should be open and show the following meals when the meals card is selected for each passenger ADT and CHD: AVML: Veg Noodles BBML: Foul Madames BLML: Chicken Shawarma CHML: Chicken Nuggets & Wedges FPML: Mixed Grill HNML: Chicken 65 LCML: Chicken Thai Curry LFML: Chicken Caesar Salad MOML: Chicken Biryani NFML: Chicken Pasta NLML: Chicken Fajita Wrap OBML: Beef & Halloumi ORML: Chicken Kabsah RVML: Greek Salad SFML: Grouper Bilkodar SPML: Group Meal VLML: Omelette
79 | When one of the meal option is selelected, each passenger (ADT and CHD) should be shown with the "+" and "-" icons
80 | When there is not availability for some meal option, the card should not be visible
81 | Show the "Continue" and "Back" buttons on the meals page
82 | Allow to select max 2 meal options per SSR
83 | Disable the "+" icon when the user has selected 2 meals
84 | Disable the "-" icon when the user has not selected meals
85 | Show the total amount for the meal(s) selected
86 | After select the meals and click on the confirm button, the meal fee should be added on the booking summary
87 | Allow to remove the meals added during booking flow
88 | When the continue button on the meals page is selected, the user should be redirected to the services page
Special Assistance
89 | When Special Assistance card is selected a popup should be open and show Wheelchair, Expectand mother, Hearing impaired and Visually impaired for each passenger ADT and CHD SSR: WCHR, PRGN, BLND, DEAF
90 | Allow to select all special asistance option
91 | Don't allow to select wheelchair when departure date is in less than 24 hours
92 | Don't show the Wheelchair option when there is not availability
93 | Add special assistance service for both flights in case of Roundtrip and Multicity
94 | After select the special assistance option and click on the confirm button, the popup should be close and the fee should be added on the booking summary
Seat Selection
95 | Show Seat Selection page with a popup informing that seats have been auto-allocated only if the booking has less than 2 passenger
96 | Show the Seat Selection page when the popup "Accept" button is clicked
97 | Infant icon appears continue to the adult name with infant
98 | Don't allow to select middle seats when the booking hast 2 or less passengers (ADT and CHD)
99 | Show "Back" and "Continue" buttons on the Seat Selection page
100 | Show seat map for each flight with the correct equipment ocnfiguration
101 | Show the allocated seat painted in the color of the seat outline
102 | Allow to remove the allocated seat by clicking on the "x" button
103 | Show an informative popup when the "Seat Legend" button is clicked
104 | Show a popup when a seat is clicked that informs the user with the seat, seat type and price and a button to select seat (if the seat is not already selected)
105 | Select the seat that was clicked when the "Select seat" button is clicked
106 | Show the family seats popup when the booking has more than 2 passengers (ADT and CHD) with "Accept" and "Discarted" buttons
107 | For family seat, when the user select a row with at least one seat occupied a pop up is shown where informed it's not possible seat together in that row
108 | Allow to select middle seats when the user accepts the family seats
109 | Rows 15 and 16 must be female only (passenger with FEM SSR)
110 | Show a a disclaimer when female seat are selected and they should be accepted
111 | Show a disclaimer when emergency seats are selected and they should be accepted
112 | Don't allow to select emergency seats (rows 12 and 14) by passenger with WCHR, DEAF or BLND
113 | The rows of Emergency exit and row 1 must not allow selection for children or adults with infants
114 | Add the seats fee on the booking summary
115 | Standar seats has amount zero when fly+ fare is selected
116 | When a popup when seats are not selected in any segment and the "Continue" button is selected
117 | Go to the Payment page when the "Continue" button is clicked
Payment
118 | Show the payment options and the Booking Summary
119 | Hide SADAD when the departure date is in less than 48 hours
120 | Show "Back" and "Continue" buttons on the Payments page
121 | Show the Voucher dropdown
122 | Display the Voucher drop-down when clicked and allow to enter the Voucher number
123 | When the Voucher number is entered, the "Apply" button is enabled
124 | Show a popup after clicking on the "Apply" button informing if the voucher is valid or not and if it does exist or does not
125 | Show Credit Shell dropdown
126 | Display the Credit Shell dropdown when clicked and allow to enter the Credit Shell PNR
127 | When the Credit Shell PNR (6 digits) is entered, the "Check Value" button is enabled
128 | Show a popup after clicking on the "Check Value" button informing if the Credit Shell covers the balance or not
129 | Don't allow to apply a Credit Shell when the email and phone number are no related with the PNR added.
130 | Hide the payment options when the voucher or credit shell cover the total of the booking
131 | Update the booking summary with amount paid and amount due when voucher or credit shell are applied.
132 | Hide SADAD when voucher or credit shell are applied and not cover the total of the booking
133 | Show the forms when Credit or Debit card are selected
134 | Show the information about SADAD when it is selected
135 | Select autocatically the credit card type when the user enters the number
136 | If the pay button is selected without check the Terms & conditions checkbox a popup should be shown informing the error.
137 | When the pay button is selected and the payment is approved the user should be redirected to the Wait page and then to the confirmation page
138 | When the pay button is selected and any error occurs, the user should be redirect to the payment page again and a popup is shown informing the error
139 | When the payment is approved, add the booking to ITINQ and SMSITIN when the booking is paid with Credit/Debit Card, Voucher and Credit Shell
140 | When the payment is approved, add the booking to ITINQ when the booking is paid with SADAD
141 | When the payment is approved, and the booking is paid with Credit/Debit Card, Voucher and Credit Shell, and email and SMS should be send (booking confirmed template)
142 | When the booking is paid with SADAD and email should be send (SADAD template)
143 | After send the email the booking should be removed from the ITINQ and SMSITIN queues
144 | A comment should be added to the booking after send the email and SMS
Confirmation
145 | Show the booking status (Pending, confirmed)
146 | Show the booking reference
147 | Show the booking information
148 | Show the payment details information
149 | Show the passenger details information
150 | Show the rental cars widget
151 | Show the banner for accommodation
MANAGE MY BOOKING
Login
153 | Allow to access MMB with the last name of any passenger on the booking (ADT and CHD)
154 | Show an informative popup when the user enter with an incorrect PNR or last name
155 | Don't allow to acess MMB with a booking created with staff (Fare Class SS)
156 | When the users enters the correct credentials, he/she should be redirected to the dasboard
Dashboard
157 | Show the booking status (Pending, confirmed)
158 | Show the booking reference
159 | Show the booking information
160 | Show the payment details information
161 | Show the passenger details information
162 | Show the accommodation banner
163 | Show the Rental cars widget
164 | If the booking is in more than 90 minutes shows the service cards: Seat Selection, Baggage, Meals, Special Assistance.
165 | If both segments (in case of roundtrip or multicity) are in less than 90 minutes, the service cards should not be shown.
166 | If all passenger in all segments (in case of roundtrio or multicity) in the booking has check-in for one segment, the service cards should not be shown.
167 | The service cards for Rental Car and Accommodation should be always shown.
168 | The lateral menu shoubl be shown with the following options: Web Check-in, Rent a car, Accommodation, Contact details, Change flights, send itinerary, passenger details
169 | If both segments (in case of roundtrip or multicity) are in less than 90 minutes, the following options should be disabled: Contact details, Change flight, Passenger details
170 | The web check-in, rent a car and accommodation should be always enabled on the lateral menu
171 | If the user access on MMB with a booking paid with SADAD with confirmation, the only option enabled on the lateral menu should be the Send itinerary
172 | If the user access on MMB with a booking already flown, the only option enable on the lateral menu should be the Send itinerary
173 | When the user access on MMB with a booking with an amound due pending to be paid, the booking summary should be shown at the bottom of the page with the option to pay the booking.
174 | With amount due the lateral menu is disabled less web checkin option
175 | The pay button on the booking summary should redirect to the payment page on MMB
176 | When one of the options in the lateral menu are not enable, a tooltip should be shown with the reason why the option is not enable: Flight already flown, amoun due pending to be paid, deparute date in less than 90 minutes.
177 | The web check-in option on the lateral menu should redirect to the login on WCI
178 | The rent a car option on the lateal menu should redirect to https://www.rentalcars.com/?affiliateCode=flyadeala503
179 | The accommodation option on the lateral menu should redirect to
180 | The contact details option on the lateral menu should redirect to the contact page on MMB
181 | The change flight option on the lateral menu should redirect to the select page on MMB
182 | The passenger details option on the lateral menu should redirect to the pax page on MMB
183 | The Seat Selection service card, should redirect to the seat page on MMB
184 | The meals card, should redirect to the meals page on MMB
Baggage
185 | Same than booking flow
186 | The baggage added in other flows are not allowed to be removed (BF or WCI)
187 | If the user access MMB with a round trip or Multicity flight and the departure date is in less than 90 minutes and return in more than 90 minutes, the user is allowed to add baggage only for the return
188 | If the user access MMB with with some passengers with check-in, the user is not allowed to update the baggage
Meals
187 | Same than booking flow
188 | The meals added in other flows are not allowed to be removed (BF or WCI)
189 | After select the meals and click on the confirm button, the user should be redirected to the dashboard and the fee should be added on the booking summary
190 | If the user access MMB with a round trip or Multicity flight and the departure date is in less than 24 hours and return in more than 24 hours, the user is allowed to add meals only for the return
191 | If the user access MMB with with some passengers with check-in, the user is not allowed to update the meals
Special Assistance
192 | Same than booking flow
193 | The special assistance option added in other flows are not allowed to be removed (BF or WCI)
194 | If the user access MMB with a round trip or Multicity flight and the departure date is in less than 90 minutes and return in more than 90 minutes, the user is allowed to add special assistance only for the return
Seat Selection
195 | Same than booking flow
196 | The user is allowed to upgrade the seat selected in other flows and pay for the difference
197 | The user is allowed to downgrade the seat selected and spoilage fee is added to the booking
198 | The user is not allowed to remove the seat selected on other flows (BF and WCI)
Change Flight
199 | Same than booking flow
200 | Allow to edit dates
201 | Allow to edit fares
202 | Don't allow to edit routes
203 | Not possible to change the type of flights (OW, RT, MC)
204 | If the flight is in less than 90 minutes, don't allow to chenge the flight
205 | If the flight already has WCI don't allow to change the flight
206 | If one journey has flown it's not possible change that journey
207 | If the booking has meals added and the user selects a flight with departure date in less than 24 hours, remove the meals and add a spoilage fee
208 | If the booking has seats added and the new flight does not have those seat available, remove the seat and add a spoilage fee
209 | When the user confirms the change a popup should be open informing about some service will be removed
210 | The price for the new flight is the differece between the new and the original flight
211 | Allow to upgrade the original flight and pay for the diference
212 | Allow to downgrade the original flight and add a apoilage fee
213 | Don't allow to change for the same flight and show the label "My flight"
214 | The CHF fee is added after 2 hours created the booking,per passenger per journey
215 | If the user change fly+ to fly the included baggage must be removed
216 | If the user change fly to fly+ a free baggage x25 kg must be added
217 | The cancel button must redirect to the dashboard page
218 | After confirm the change, add the change flight fee
219 | If the user changes the flight within 2 hours of booking creation dont add the change fee
220 | After confirm the change, the booking summary should be shown at the bottom of the page and the button should redirect to the payment page
Change Contact
221 | Same than booking flow
222 | Don't allow to edit title, first and last name
223 | Allow to edit country of residence, City, country code, phone or mobile number, email address and confirm emails address
224 | If the user access to the change contact page with a booking without tile, first name or last name added, the user should be allowed to add the information for this fields.
225 | Show the SMS option selected by default
226 | Show the marketing opt-in option selected by default
227 | Don't add any amount for the change contact
228 | Show back and continue buttons
229 | Show an informative popup when the "Continue" button is selected without add the mandatory information
230 | After confirm the change, the continue button should redirect to the payment page
Change passenger
231 | Same than booking flow
232 | Don't allow to edit title, first and last name and date of birth
233 | Allow to edit Nationality, Document type, Issuing country, document number and expiry date
234 | If the user access to the change passenger page with a booking without tile, first name or last name or date of brith added, the user should be allowed to add the information for this fields.
235 | Show the Hijri calendar on date of birth and expiry date fields
236 | Don't add any amount for the change contact
237 | Show back and continue buttons
238 | Show an informative popup when the "Continue" button is selected without add the mandatory information
239 | After confirm the change, the continue button should redirect to the payment page
Resend Itinerary
240 | When Send itinerary is selected on the lateal menu, a popup should be shown informing the user that the itinerary has been send (booking updated template)
241 | The booking should be added to the ITINQ and SMSITIN (if applies) queues
242 | The email and SMS should be received in the language which was created the booking
243 | After send the email the booking should be removed from the ITINQ and SMSITIN queues
244 | A comment should be added to the booking after send the email and SMS
Payment
245 | Same than booking flow
246 | Show the payment methods except SADAD
247 | If there is not amount due pending to paid, don't show any payment method
248 | Show the "Back" and "Paid" button
249 | When the pay button is selected and the payment is approved the user should be redirected to the Wait page and then to the dashboard page
250 | When the pay button is selected and any error occurs, the user should be redirect to the payment page again
251 | When the payment is approved, add the booking to ITINQ and SMSITIN when the booking is paid with Credit/Debit Card, Voucher and Credit Shell
252 | If there is a declined payment, the booking should be added to the BALDUE queue
253 | When the booking is added on the BALDUE queue, an email and SMS should be send (unbalance booking template)
254 | When the payment is approved, and the booking is paid with Credit/Debit Card, Voucher and Credit Shell, and email and SMS should be send (booking updated template)
255 | After send the email the booking should be removed from the queue (BALDUE, ITINQ or SMSITIN)
256 | A comment should be added to the booking after send the email and SMS
WEB CHECK-IN
Login
257 | Allow to access WCI with the last name of any passenger on the booking (ADT and CHD) | Checkin only available between 24- 48 hours before the flight
258 | Show an informative popup when the user enter with an incorrect PNR or last name
259 | Don't allow to acess WCI with a booking created with staff (Fare Class SS)
260 | When the users enters the correct credentials, he/she should be redirected to the dasboard
Select flight and passenger
261 | Show the description of the page - Please select the passengers you want to check-in and get the boarding pass for. - Web check-in is not available for passenger who requested special assistance. Please check-in at the airport - Remember once you check-in no further changes may be made to your flight. | When the user is already checked the checkbos is disabled
262 | Show the "Back" and "Continue" button
263 | Show the flight information
264 | Show the list of passengers ADT and CHD with the checbox enable if the flight is on more than 48 hours
265 | If the flight is in more than 48 hours shows a message indicating the check-in is not available and the checkbox disable
266 | If the passenger has any special assistance service added, shows a message indicating the check-in is not available and the checkbox disable
267 | If the passenger has seat added, shows the seat number
268 | A popup should be shown when the continue button is selected without select any passenger
269 | when the passenger and the continue button are selected, a popup should be shown informing about the terms and conditions
270 | If the chexbox on the terms and conditions popup is not selected the user is not allowed to continue with the flow
271 | If the passenger accepts the terms and conditions and selects the continue button, the user should be redirected to the passenger page
272 | If the passenger has completed the WCI for a domestic route, the link to download the boardingpass should be shown
273 | The Boarding Pass should PDF should open in a new tab
274 | If the passenger has completed the WCI for an international route, the link to download the boardingpass should not be shown and the disclaimer should appear.
Passenger details
275 | Show the Adult 1 passenger details
276 | Show the "Back" and "Continue" button
277 | The first name, last name and birth date cannot be edited
278 | The travel document information can be edited
279 | Show a popup informing that some of the required information is wrong when the passenger information or even the travel documents is/are wrong | The yakeen pop up has the same behavior as in booking flow
280 | Come back to the select flight page when the "Back" button is clicked
281 | Go to the Services page when the "Continue" button is clicked and the missing information is completed well
Services
282 | Same than booking flow
283 | Special Assistance card should not be shown
Baggage
284 | Same than booking flow
285 | The baggage added in other flows are not allowed to be removed (BF or WCI) | In the baggage card only can see the passengers and journeys selected for check-in
286 | If the user access WCI with a round trip or Multicity flight and the departure date is in less than 90 minutes and return in more than 90 minutes, the user is allowed to add baggage only for the return | The subtotal in baggage card only shown the baggage for the passenger selected for checkin in the journeys selected
287 | If the user access MMB with with some passengers with check-in, the user is not allowed to update the baggage
Meals
286 | Same than booking flow
287 | The meals added in other flows are not allowed to be removed (BF or WCI)
288 | After select the meals and click on the confirm button, the user should be redirected to the dashboard and the fee should be added on the booking summary | In the meals card only can see the passengers and journeys selected for check-in
289 | If the user access WCI with a round trip or Multicity flight and the departure date is in less than 24 hours and return in more than 24 hours, the user is allowed to add meals only for the return | The subtotal in meals card and meal option only shown the baggage for the passenger selected for checkin in the journeys selected
290 | If the user access MMB with with some passengers with check-in, the user is not allowed to update the meals
Seat Selection
291 | Same than booking flow
292 | The user is allowed to upgrade the seat selected in other flows and pay for the difference
293 | The user is allowed to downgrade the seat selected and spoilage fee is added to the booking
294 | The user is not allowed to remove the seat selected on other flows (BF and MMB)
295 | The user is not allowed to continue if he/she does not have seat assigned | A pop up is shown when this happened
296 | If the user has not assigned seats, the autoassigment should apply without show the popup | Autoassigment seats in this flow are free
297 | The user is not allowed to remove the seat selected on other flows (BF and WCI)
Payment
298 | Same than booking flow
299 | Show the payment methods except SADAD
300 | If there is not amount due pending to paid, don't show any payment method
301 | Show the "Back" and "Paid" button
302 | When the pay button is selected and the payment is approved the user should be redirected to the Wait page and then to the dashboard page
303 | When the pay button is selected and any error occurs, the user should be redirect to the payment page again
304 | When the payment is approved, add the booking to WBCKIN and SMSCKN the booking is paid with Credit/Debit Card, Voucher and Credit Shell
305 | If there is a declined payment, the booking should be added to the BALDUE queue
306 | When the booking is added on the BALDUE queue, an email and SMS should be send (unbalance booking template)
307 | When the payment is approved, and the booking is paid with Credit/Debit Card, Voucher and Credit Shell, and email and SMS should be send (boardingpass template)
308 | After send the email the booking should be removed from the queue (BALDUE, WBCKIN, SMSCKN)
309 | A comment should be added to the booking after send the email and SMS
Confirmation
310 | Show the flight information
311 | Show the list of passengers selected to complete the check-in
312 | Show the seat assigned in other flows or in WCI
313 | If the passenger has completed the WCI for a domestic route, the link to download the boardingpass should be shown
314 | The Boarding Pass should PDF should open in a new tab
315 | If the passenger has completed the WCI for an international route, the link to download the boardingpass should not be shown and the disclaimer should appear.
316 | When the user selects the continue button, he/she should be redirected to the flight and passenger selection page
Boarding Pass
317 | The booking reference should be shown | Boarding pass is download in the language which the booking was created and not the language the user select fot checkin
318 | The barcode should be shown and correspond with the booking
319 | The passenger name should be shown
320 | The flight information should be shown: Dates, routes, Boarding closes, boarding time, flight number, seat number, gate, seq number
321 | Services information: Include baggage type, meals and infant
322 | Important information
323 | Bardcode and flight information
324 | Baggage allowance banner
MEMBERS
Login
321 | Allow to login with the email and password for members
322 | Forgot password open the forgot password form.
323 | Sign up: Direct Access for users who want to register.
324 | Sign-in button: The button will be enabled.
325 | When entering the wrong data in the fields, they will be marked in red.
326 | The Sign-in functionality will be shown in the header located in the home and corporate pages and in the standalone page. | The home has a space below the home search to access the standalone page
327 | The functionality should be the same in the modal and in the standalone page.
328 | Incorrect credentials: In the case of entering incorrect credentials, it should show an error message without indicating the specific error.
329 | Account locked: When entering with an existing but blocked account, you must display an informational message indicating that the account is locked.
330 | Account pending to activate: An error message will be displayed specifying that the account is pending activation.
Register
331 | Allow to register with the email and password for members
332 | When entering the wrong data in the password fields, it will be marked in red and the correct way to enter the data will be indicated.
333 | The password field should show the icon to visualize the password data.
334 | Do you already have a code?: Direct access to the form in which the token is entered in case a user already has a valid code that he previously requested.
335 | Sign in: Direct access to the login for lost users.
336 | Register button: The button will be enabled once the information entered in the fields has a valid format.
337 | When entering the wrong data in the fields, they will be marked in red.
338 | If the user enters the data and closes the modal when the modal is open again the information added previously should be shown.
339 | The Sign-up functionality will be shown in the header located in the home and corporate pages and in the standalone page.
340 | The functionality should be the same in the modal and in the standalone page.
341 | Once the user completes the registration process, a message informing that a validation code will be sent to the email. This must have the user´s name
342 | If the user adds an email associate to one account already create, a message will be shown informing about the problem.
Token/Code validation to complete the registration
343 | The code validation modal consist of: Code field, submit button, back to register
344 | If the user enters invalid data, a popup will be shown informing the problem.
345 | The code validation functionality will be shown on the modal and standalone page.
346 | Once the code validation is entered correctly, the user is redirected to complete your registration page.
347 | The token/code has an expiration time of 3 hours (config at DEV level).
348 | When the user entered a token already used before, an exception should be shown informing the error.
349 | At this point, the user account is activated. The user account is created in Navitaire once a valid token is entered.
350 | The user is saved in Navitaire with WWMB role.
Complete the registration
351 | This page offers the following: Account details and personal details
352 | The account details shows the emails without the possiblity to edit it.
353 | Personal details shows; Gener, Title by default MR, First and last name, Date of birth, Nationality
354 | GDPR policy checkbox. Mandatory. Link https://www.flyadeal.com/en/information/legal/cookie-policy/
355 | The submit button should be disabled until all mandatory information is added.
356 | Once all mandatory information is added, and the submit button is clicked a message will be shown informing the data has been saved.
357 | The header, footer, and breadcrumb should be the same as corporate pages.
User menu
358 | The user menu will be placed in the header, like a dropdown menu.
359 | When the user is logged-in is identified by username in the header. This menu is only visible when the user is logged-in, until then, its place is normally occupied by the login component.
360 | The Menu component should show the following section: Home, Bookings, My profile, My account, contact details, travel documents, logout
361 | Bookings redirects to the bookings page
362 | My profile redirects to the profile page
363 | My account redirects to basic - preferences page
364 | Contact details redirect to the contact details page
365 | Travel document redirect to the travel document page
366 | Logout redirects to the home page without the user logged-in
Contact details page
367 | The Contact details page should show the following section: Country of residence, City, Email address, country code, phone or mobile number, submit button
368 | The header, footer, and breadcrumb should be the same as corporate pages
369 | Users entering the page for the first time: The form should be displayed with all fields empty and the Submit button must be disabled
370 | When entering data, in case of failure, the invalid fields will be highlighted, the submit button will only be activated when all the fields are correctly filled out and in case of success, a success popup will be displayed
371 | If there are previously stored data, the form is displayed completely with the existing information. All the changes that are made are validated and saved in the PSS.
Travel documents page
372 | The Travel documents page should show the following section: Document type selector, Issuing country selector, Expiration date, Number, default document radio button, add document button, delete button, confirmation popup, submit button
373 | The header, footer, and breadcrumb should be the same as corporate pages
374 | The user will be possible to add/delete multiple travel documents.
375 | It can have a maximum of 5 forms when it reaches its maximum, the Add Document button should disappear
376 | Users entering the page for the first time, the form should be displayed with all fields empty, the Add document button must be enabled and the Submit button must be disabled
377 | In case of failure, the invalid fields will be highlighted
378 | The submit button will only be activated when all the fields are correctly filled out.
379 | In case of Add document must display a new form like the one shown by default when you enter the page
380 | In case of deleting a form, a confirmation popup will be displayed
381 | In case of success, a success popup will be displayed
382 | If there are previously stored data, the form is displayed completely with the existing information. All the changes that are made are validated and saved in the PSS.
Booking List
383 | List of bookings with at least some upcoming flight, pending to be flown sorted by departure date.
384 | The upcoming list also includes canceled and hold bookings (hold-cancel will not be included).
385 | List of bookings with all flights flown.
386 | Booking info cards: PNR, date of departure, stations. Sort for date departure.
387 | One card per segment is shown e.g. if OW, only one card is shown, if RT, two cards are shown
388 | Each Booking must have links to access MMB and WCI. Always available and active. Except for “Past flights” list, deeplink to WCI will not be included
389 | By clicking any of the available options you will be redirected to the Home page of the selected flow through a deeplink.
390 | Display order by departure date descendant (oldest last).
391 | When no results: If any of the sections do not have bookings available, display a message informing the user.
Preferences page
392 | The Basic preference page should show the following section: Title, language, currency, departure city
393 | Language prefilled by default AR
394 | Currency prefilled by default SAR
395 | The header, footer, and breadcrumb should be the same as corporate pages
396 | Language and currency options in the drop-downs will be filterable as users input characters in the box.
397 | f the data is changed, when the form is entered again, the edited information is displayed. All the changes that are made are validated and saved in the PSS.
398 | Special Assistance option should be added to the current Basic preferences page
399 | Any option for special assistance should be selected by default
400 | The special assistance option should be shown the following options as it does in BF: Wheelchair, Expectant mother, Hearing impaired, Visually empaired
401 | The selection functionality and additional information displayed according to the type of assistance selected must be equal to that of BF. eg. Expectant mother
402 | When the option is selected and the save button is clicked, a popup should be shown indicating the changes have been saved.
Forgot and reseat password
403 | The forgot password form will be composed by: Email, Back to login: Allows user to return to login page, I already have a code, Submit button
404 | When entering the wrong data in the fields, they will be marked in red.
405 | IBE validates if there is an account for the username entered, in which case it obtains the email associated with the account and starts the double opt-in process for security reasons
406 | The email validation functionality will be shown in the modal and standalone page.
407 | Once the email is entered correctly, a message will be shown informing an email has been sent.
408 | The Forgot password email should be sent. This must-have name´s user.
409 | User inputs token code in the forgot password token input field.
410 | In case of an invalid token, show an informative error message.
411 | User inputs new password (only once, no need to repeat but we offer the “eye” icon instead).
412 | If the password criteria are not satisfied, the error will be informed while typing.
413 | Do not allow submit until matches it.
414 | No extra validations are required (i.e. cannot repeat password).
415 | The system updates the new password, clicking the Save button redirects the user to the profile form.
Booking Flow
416 | The same as anonymous users
417 | If the user has stored special assistance in his/her profile, they should be selected by default only for the user logged-in when he/she goes to the services page and the amount added in the booking summary depends on the fare selected on the Select Flight page.
417 | The details of the first pax and the contact details will be previously filled in, with all the data available in the user profile.
418 | Automatically fill in the data of the available travel documents with the document selected by default in the profile.
418 | If the data is modified in the booking flow, the profile data is not modified (only the reservation information).
419 | If the user is logged in and complete a booking, it should be linked to the user ID who created the booking.
Manage my Booking
420 | The same as anonymous users
421 | If the user has stored special assistance in his/her profile, they should be selected by default only for the user logged-in when he/she goes to the services page and the amount added in the booking summary depends on the fare selected on the Select Flight page.
Web Check-in
422 | The same as anonymous users
AGENCIES
Login
423 | The login for agencies is located on the login module for memebers
424 | Allow to login with the email and password for agents
425 | Once the user is logged successfully, he/she should be redirected to the booking list page.
426 | Incorrect credentials: show error message informing the error
427 | Blocked account: show an error to inform the account is blocked
428 | It should not allow you to log in to a member account on agent login
429 | Forgot password open the forgot password form.
User menu
430 | When logged-in, is identified by an icon + username
431 | When not logged-in: the menu is only visible when the user is logged in. Until then, its place is normally occupied by the login component.
432 | The menu is located In the header, like a dropdown menu.
433 | The following options should be shown on the menu: Make a booking, Bookings, My profile and logout
434 | Make a booking: link to the home page where the search component is available
435 | Bookings: go to the Bookings List page.
436 | My profile: agent’s profile
437 | Logout: logs the users out of the agency portal and redirects them to the home page
Booking List
438 | Once the user is logged successfully, he/ she will be redirected to the booking list page
439 | On the first load. no bookings will be listed (no need for auto-search with no filters).
440 | The following fields should be shown: Record Locator, Contact name, Creation date from, Creation date to, Submit button, Reset form button, Show more filters, My booking table
441 | Once the “Show more filters” label is clicked the following fields should be displayed: Booking status (All, Confirmed, Hold, Canceled), Select Origin, Select destination, Agent Name, Contact email
442 | The “Show more filters” label change to “Show less filters” and when It is clicked the previous fields are hidden.
443 | Agency agent (TAGT): can see only their bookings
444 | Agency admin agent (TMST): can see bookings from any agent of its agency (including himself if created any)
445 | Once the user applies any filter and clicks on the “Search” button, the result should be shown in the table.
446 | The table should show the following information: PNR, Origin, Destination, Departure date, Arrival date, Status, Agent Name (only for master agents), Pax info list (Full name), Actions: Options available: MMB and WCI (The option is a link that redirects to the page through a deep link)
447 | No results: a message must be displayed in case no result is found
448 | If the user clicks on “Reset form” the table should not show results.
Forgot and reset password
449 | The forgot password form will be composed by: Email, Back to login: Allows user to return to login page, I already have a code, Submit button
450 | Once the user fills the form with their email a message should be shown
451 | IBE validates if there is an account for the username entered, in which case it obtains the email associated with the account and starts the double opt-in process for security reasons
452 | A security token is generated and linked to the account requesting the forgot password. By default, its lifetime is set for 3 hours
453 | An email is sent to the user’s email address with the token.
454 | After the forgot password process, the website informs the user that an email has been sent to the user’s email address to proceed with the reset password process and displays a new input field for the user to input the received token.
455 | User opens email, gets token and goes back to IBE website to validate token.
456 | User inputs token in input field
457 | In case token valid, user is redirected to reset page where to input the new password.
458 | The user inputs their new password (only once, no need to repeat but we offer the “eye” icon instead).
459 | The system updates the new password and redirects the user to the booking list page.
460 | In case an invalid or expired token, show an informative error message.
Agency profile
461 | Agent will have access to retrieve the credit information available as the total amount and currency (read-only).
462 | The currency and total amount are only managed by PSS
463 | The Agency profile page will contain two sections of information: Organization information and Agent Contact
464 | Organization info, Read-only
465 | The access to this section needs to be located in the web header, listed on the user menu as “My profile”
466 | he information must be displayed in a pre-populated form, with the existing information in the PSS.
467 | Form fields for Agency info: Organization code, agency name and organization name
468 | There must exist a section where the user contact information can be edited
469 | The access to this section needs to be located in the web header, listed on the user menu as “_My profile_”
470 | The information must be displayed in a pre-populated form, with the existing information and all changes must be validated and saved in the PSS when submitting
471 | By clicking submit the validation will run
472 | In case of failure, the invalid fields will be highlighted
473 | In case of success, a popup will be displayed
474 | The contact details field should be the same as anonymous users.
Booking Flow
475 | Same than anonymous
477 | Prefill contact details automatically, with all available data in user profile, don’t wait for user to request
479 | All the fields available on the agent profile should be prepopulated
481 | If changes, the profile doesn’t get changed (only booking info).
Manage my Booking
482 | Same than anonymous
Web Check-in
483 | Same than anonymous
Payment B2B
484 | Credit payment is an option offered to Agents at the Payment step. Some conditions should be validated in order to offer (or not) this option to the user. When not available, will be hidden.
486 | It will only be offered for Agents with a credit greater than the total amount outstanding, but not for Agents who have logged in without sufficient credit.
488 | Flow: BF, MMB, WCI
490 | In the Credit payment section, the user should see as informative (read-only)
492 | Their current account’s credit total amount o New booking/changes total amount to be deducted from their account.
494 | Credit payment should be selected by default.
496 | Show a checkbox + text, which could include a link to another page.
498 | Terms & contidionts should be mandatory to complete the payment.
500 | When the T&C check is not marked, it is marked in red and shows a popup informing that there is missing data to fill.
502 | When making the payment, the agent cannot exceed its available amount (their current balance).
504 | The booking must be set as Confirmed with the new Credit payment added. Credit must be deducted from the user’s account
506 | In case of exception, show an informative error to the user and let them retry payment with Credit or any other method.

## BF - Deliveries
*Note: Follow the checklist plan to validate all the cases Red: delivery not approved Yellow: delivery not tested Green: delivery approved Grey: doesn't apply
BOOKING FLOW
BF1: Trip Type | Comments | Test
One Way - 1 ADT - HOLD |  | JMeter
Round Trip - 1 ADT - HOLD |  | JMeter
BF2: Passenger Types | Comments | Test
One Way - 1 ADT + 1 CHD - HOLD |  | JMeter
RoundTrip - 1 ADT + 1 CHD + 1 INF - HOLD |  | JMeter
One Way - 2 ADT + 1 CHD + 2 INF - HOLD | One infant per passenger ADT | JMeter
RoundTrip - 3 ADT + 6 CHD + 3 INF - HOLD | Max 9 pax between ADT and CHD | JMeter
One Way - 9 ADT + 9 INF - HOLD |  | JMeter
RoundTrip - 5 ADT + 4 CHD + 5 INF - HOLD |  | JMeter
BF3: Routes | Comments | Test
One Way 1 ADT - Domestic - HOLD |  | JMeter
RoundTrip 1 ADT - International- HOLD | International routes: Dubai and Kuwait. It will be tested once DEV4 is available | JMeter
One Way 1 ADT + 1 CHD + 1 INF - Domestic - HOLD |  | JMeter
RoundTrip 1 ADT + 1 CHD + 1 INF - International- HOLD |  | JMeter
One Way 3 ADT + 4 CHD + 2 INF - Domestic - HOLD |  | JMeter
RoundTrip 5 ADT + 2 CHD + 5 INF - International- HOLD | It will be tested once DEV4 is available. | JMeter
BF4: Fares | Comments | Test
One Way 1 ADT - fly - HOLD |  | JMeter
RoundTrip 1 ADT - fly+ - HOLD |  | JMeter
BF5: Passenger Information | Comments | Test
One Way/RoundTrip 1 ADT + 1 CHD - HOLD | Does not apply to Igor's development, that is something that the F3 custom should validate Not applicable for Jmeters. CHD not allowed to travel with and ADT under 16
One Way/RoundTrip 1 ADT + 1 INF - HOLD | Does not apply to Igor's development, that is something that the F3 custom should validate Not applicable for Jmeters. INF under 8 days is not allowed to travel
BF6: Travel Documents | Comments | Test
One Way 1 ADT - International - Passport - HOLD | International routes only passport allowed. It will be tested once DEV4 is available (May 7th). | JMeter
RoundTrip 1 ADT - Domestic - Iqama - HOLD | Nationality different than Saudi Arabia | JMeter
One Way 1 ADT - Domestic - National ID - HOLD | Saudi Arabia nationality | JMeter
RoundTrip 1 ADT - Domestic - Passport - HOLD | Nationality different than Saudi Arabia | JMeter
BF7: Payment | Comments | Test
One Way 1 ADT - SADAD | SADAD available for domestic origin and departure >48 hours | JMeter
RoundTrip 1 ADT + 1 CHD - Visa (non 3DS) |  | JMeter
One Way 1 ADT + 1 CHD + 1 INF - MasterCard (3DS) |  | Manual
RoundTrip 2 ADT + 1 INF - Voucher (Full payment) |  | JMeter
One Way 3 ADT + 4 CHD + 2 INF - Credit Shell (Full payment) | PNR used for Credit Shell should have the same email and phone number than the current booking | Manual
RoundTrip - 3 ADT + 6 CHD + 3 INF - Voucher/Visa |  | Manual
One Way 3 ADT - Credit Shell/MasterCard |  | Manual
RoundTrip - 5 ADT + 4 CHD + 5 INF - Voucher/Credit Shell |  | Manual
BF8: Baggage | Comments | Test
One Way 1 ADT - fly - 1xBaggage 25 Kg - PAID |  | JMeter
RoundTrip 1 ADT - fly+ - 1xBaggage 25 Kg - PAID | fly+ has one baggage 25Kg included | JMeter
One Way 1 ADT + 1 CHD + 1 INF - fly - 2xBaggage 25 Kg - PAID | Max 2 baggages per type added per passenger ADT and CHD | JMeter
RoundTrip 3 ADT +2 CHD + 2 INF - fly+ - 2xBaggage 25 Kg - PAID | Fee added only for 1 baggage | JMeter
One Way 1 ADT - fly - 1xBaggage 15Kg - 1xBaggage 25Kg - PAID |  | JMeter
BF9: Meals | Comments | Test
RoundTrip 1 ADT - 1xMeal - PAID | Meals is not available for flights with departe < 24 hours | JMeter
One Way 3 ADT - 1xMeal - PAID |  | JMeter
RoundTrip 1 ADT + 1 CHD + 1 INF - 2xMeals - PAID | Max 2 meals per type added per passenger ADT and CHD | JMeter
One Way 3 ADT +2 CHD + 2 INF - 2xMeals - PAID |  | JMeter
BF10: Special Assistance | Comments | Test
RoundTrip 1 ADT - WCHR - PAID | WCHR: Wheelchair. Not allowed for flights with departure <24 hours. Special assistance has fee zero. Allowed for ADT and CHD. Added automatically for return in case of Round Trip | JMeter
One Way 3 ADT - PRNG - PAID | PRNG: Expectand mother | JMeter
RoundTrip 1 ADT + 1 CHD + 1 INF - BLND - PAID | BLND: Hearing impaired | JMeter
One Way 3 ADT +2 CHD + 2 INF - DEAF - PAID | DEAF: Visually impaired | JMeter
RoundTrip 3 ADT +2 CHD + 2 INF - WCHR+PRNG+BLAND+DEAF - PAID |  | JMeter
BF11: Seatmap | Comments | Test
One Way 1 ADT - fly - Autoassigment - PAID | Middle seats disable | JMeter
RoundTrip 1 ADT - fly+ - Autoassigment - PAID |  | JMeter
One Way 1 ADT + 1 CHD - fly - Standard Seat / Standard plus- PAID |  | JMeter
Roundtrip 1 ADT + 1 CHD - fly+ - Standard Seat / Front Row Premium- PAID | Standar Seat included on the fare | JMeter
One Way 1 ADT + 1 INF - Extra leg room / Speedy Exit- PAID | INF not allowed to seat on Row 1 and emergency exit (rows 12 and 14). Passenger with special assistance not allowed to seat on emergency exit | JMeter
RoundTrip 1 ADT + 1 CHD - Female seat - PAID | Female seat only allowed for ADT and CHD with title MRS, MS, MISS. Female seat allowed for CHD with title MASTER if the booking has a female ADT | JMeter
One Way 2 ADT + 1 CHD - Family seats - PAID | Family seats allowed for booking with more than 2 passengers ADT and CHD. Middle seats enable. Passenger should be together depending on rules | JMeter
BF12: Multicity | Comments | Test
Multicity - 1 ADT - PAID | Arrival for frist flight should be the same than departure for second flight | JMeter
Multicity - 1 ADT + 1 CHD - PAID |  | JMeter
Multicity - 1 ADT + 1 CHD + 1 INF - PAID |  | JMeter
Multicity - 3 ADT + 5 CHD + 2 INF - PAID |  | JMeter
BF13: Promocode | Comments | Test
One Way 1 ADT - Promocode - PAID |  | JMeter
RoundTrip 1 ADT + 1 CHD - Promocode - PAID |  | JMeter
Multicity 1 ADT + 1 CHD + 1 INF - Promocode - PAID |  | JMeter
Multicity 3 ADT + 2 CHD + 3 INF - Promocode - PAID |  | JMeter

## MMB - Deliveries
*Note: Follow the checklist plan to validate all the cases Red: delivery not approved Yellow: delivery not tested Green: delivery approved Grey: doesn't apply
MANAGE MY BOOKING
MMB1: Login
MMB2: Change Flight
MMB3: Payment
MMB4: Baggage
MMB5: Meals
MMB6: Special Assistance
MMB7: Seat Map
MMB8: Change Contact
MMB8: Change Passenger
MMB10: Resend Itinerary

## WCI - Deliveries
*Note: Follow the checklist plan to validate all the cases Red: delivery not approved Yellow: delivery not tested Green: delivery approved Grey: doesn't apply
WEB CHECK IN
WCI1: Login | Comments
WCI2: Select pax & flights | Comments
WCI4: Passenger details | Comments
WCI4: Payment | Comments
WCI5: Baggage | Comments
WCI6: Meals | Comments
WCI7: Seatmap
WCI8: BoardingPass | Comments
One Way/RoundTrip - Domestic | Allowed to download the BoardingPass
One Way/RoundTrip - International | Not allowed to download the BoardingPass

## B2C - Deliveries
*Note: Follow the checklist plan to validate all the cases Red: delivery not approved Yellow: delivery not tested Green: delivery approved Grey: doesn't apply
B2C
B2C1: Register
B2C2: Login
B2C4: Booking Flow
B2C4: Manage my Booking
B2C5: Web Check-in
B2C6: Profile
B2C7: Contact details
B2C8: Travel documents
B2C9: Booking List
B2C10: Preferences page
B2C11: Forgot and reseat password

## B2B - Deliveries
*Note: Follow the checklist plan to validate all the cases Red: delivery not approved Yellow: delivery not tested Green: delivery approved Grey: doesn't apply
B2B
B2B1: Login
B2B2: Booking Flow
B2B3: Manage my Booking
B2B4: Web Check-in
B2B5: Payment
One Way/RoundTrip 1 ADT - Agency Credit
One Way/RoundTrip 1 ADT + 1 CHD - Visa (non 3DS)
One Way/RoundTrip 1 ADT + 1 CHD + 1 INF - MasterCard (3DS)
B2B6: Booking List
B2B7: Forgot and reseat password
B2B8: Agency Profile

## TEST Data
CREDIT AND DEBIT CARD |  | Promocode | Document Type | Document number | Date of birth, Nationality or Visa issue year | Passenger Type | Document Type | Yakeen validation
Success Visa ( 3DS ) / Success Refund | 4557012345678902 05/21 123 | TEST20 | National ID | 1069959896 | 1981-05-16 | Adult | National ID | ID number | Date of birth
Success MasterCard ( 3DS ) / Success Refund | 5313581000123430 05/21 CVV : 123 | PROMOS20 | National ID | 1085539433 | 1992-07-24 | Adult | Passport (Citizen) | Passport number | Date of birth
Success VISA ( non-3DS ) / Success Refund | 4012000033330026 05/21 123 | UAT1 | National ID | 1099901512 | 1997-07-01 | Adult | Passport (Foreign) | Passport number | Nationality
Success MADA (3DS) / Refund | 5297412542005689 05/21 350 | UAT2 | Passport (Citizen) | P257928 | 1981-05-16 | Adult | Travel Visa | Visa Number | Visa issue year
MasterCard 3DS | 5323543352220584 05/21 123 | UAT3 | Passport (Foreign) | XDC35961 | Spain | Adult - Child - Infant | Iqama | Iqama number | Date of birth
|  |  | Passport (Foreign) | 540675805 | British | Adult - Child - Infant
VOUCHERS |  |  | Passport (Foreign) | J5997578 | India | Adult - Child - Infant
# | Valor |  | Passport (Foreign) | 761288527 | United Kingdom | Adult - Child - Infant
10096450060500001 | 700 |  | Travel Visa | X | X | Adult
10096457078700002 | 700 |  | Iqama | 2443697533 | 1968-05-19 | Adult
10096461477300001 | 2000 |  | Iqama | 2461090868 | 12-Dic-1987 | Adult
10096464716300002 | 2000 |  | Iqama | 2177536261 | 1978-02-01 | Adult
10096465488600003 | 2000 |  | Iqama | 2235685795 | 1970-06-30 | Adult
10096462810700004 | 2000 |  | National ID | 1167272341 | 18/01/2014 | Child
|  |  | Passport (Citizen) | W304379 | 21/02/2012 | Child
|  |  | Travel Visa | X | X | Child
|  |  | Iqama | 2467369522 | 2018-08-30 | Child
|  |  | National ID | 1196729808 | 2020-04-20 | Infant
|  |  | Passport (Citizen) | Y110284 | 17/09/2019 | Infant
|  |  | Travel Visa | X | X | Infant
|  |  | Iqama | 2467369522 | 30-Agos-2018 | Infant